# RBA OPMO Monthly Makgotla Report – August 2016

# Community Events scheduled in the coming month

# (1/8/2016 – 31/8/2016)

| Event Name | Region | Date |
| --- | --- | --- |
| HSDS: Letsema (Community Outreach, Occupational health) | South East | Friday, 26 August 2016 |
| RBED: Farmers market session | Capital | Saturday, 27 August 2016 |
| North East Primary Schools Football & Netball League Round 5 | North East | Wednesday, 31 August 2016 |
| TENDER: Waste Management (Refuse Collection) | All | Wednesday, 31 August 2016 |

# Big Projects (Currently Active)

# (As at 14/8/2016)

| Project Name | Responsible Department | Budget Source | Progress % | End date | Region; Village |
| --- | --- | --- | --- | --- | --- |
| Establishment of OVC (Orphans & Vulnerable Children) in Luka | HSDS | External Funding | 42.5% | 11 November 2016 | North; Luka |
| Population and Use of Land Audit (PULA) 2016 | Research | RBN & External Funders | 10% | 15 December 2016 | All |
| Monitoring Construction of a Road in Tsitsing & Storm Water Drainage | Infrastructure Maintenance (IDP project) | RLM | 94.3% | 31 August 2016 | North East; Tsitsing |
| Focused Approach -Enterprise Development Phase 1 | RBED | External Funders | 55.8% | 30 December 2017 | All |
| Land Policy Development | Traditional Governance | RBN | 88.1% | 8 August 2016 | All |
| Establishment of cooperatives at the sheltered employment centre | HSDS | RBN | 71.8% | 18 July 2016 | Capital; Lefaragathla |
| Establishment of mini market in RBN | Land Use & Agriculture | RBN | 64% | 29 July 2016 | North & Capital; Luka & Phokeng |
| Plan 35 Development | GCOO | RBN | 51.6% | 19 November 2016 | All |
| Establishment and Management of the animal pound/feedlot in Bafokeng | Land Use & Agriculture | RBN | 61.3% | 17 October 2016 | North East; Tlaseng |
| Lefaragathle Old Pump House Upgrade | Infrastructure Maintenance | RBN | 46% | 13 October 2016 | Capital; Lefaragathla |
| Preparations for Olympics Rio 2016 | RBS | RBN | 81% | 29 July 2016 | Capital; Phokeng, Lefaragatlha |
| Monitoring the Standard Bank Housing Project | Infrastructure Maintenance | RLM | 63.7% | 30 August 2016 | North, Capital; Luka, Mogono, Phokeng, Kgale |
| Monitoring the Construction of High-mast Lighting in RBN Villages (IDP project) | Infrastructure Maintenance | RLM | 83.7% | 12 August 2016 | North, Central, South East; Kanana, Seutube, Marakana & Mosenthal, Mabitse, Tlapa & Tlapa East, Rasimone, Lesung, Mafika, Robega |
| Marketing for Bafokeng Tourism Establishments | RBED | RBN | 59.1% | 29 August 2016 | All |
| Establishment of Community and Nutrition and Development Center (CNDC) Project | HSDS | RBN | 39.9% | 18 October 2016 | Central, Capital; Kanana, Lefaragatlha |
| Kimberley pilgrimage | Arts & Culture | RBN | 45% | 12 October 2016 | All |

# Projects scheduled to start in the coming month

# (1/8/2016 – 31/8/2016)

| Project Name | Responsible Department | Budget Source | Planned Benefits | Region |
| --- | --- | --- | --- | --- |
| Big Walk/Fun Run 2016 | RBS | RBN | Commemoration of women’s month and encourage healthy living among women | All |

# Projects completed in the previous month

# (1/6/2016 – 30/6/2016)

| Project Name | Responsible Department | Budget Source | Actual/ Realised Benefits | Region; Village |
| --- | --- | --- | --- | --- |
| NGO Profiling on Enterprise Development Module | Strategic Reations | RBN | Up-to-date and manageable database of all NGOs | All |
| Monitoring Tlaseng Construction of Roads & Storm Water Drainage Phase 3 | Infrastructure Maintenance | RLM | 1.5kms of new paved roads | North East; Tlaseng |
| Reception and Call Centre System Implementation: Phase1 | Municipal Services | RBN | Automated recording and reporting on calls received and statistics | Capital; Phokeng |
| Kgotha Kgothe May 2016 | Traditional Governance | RBN | 1323 community members attended; 80 members of youth were employed; and 15 SMMEs were appointed | All |
| Child Protection Awareness Campaign | HSDS | RBN | 1 SMME was appointed; possible reduction in child abuse and neglect | All |

# Procurement Spend on Local SMMEs by mines and RBN Entities

|  | Procurement Spend |  |  |
| --- | --- | --- | --- |
|  | June only | Year-to-date (Jan – June) | % of total Procurement Spend (YTD) |
| Impala | R 0.00 | R194 608 837.00 | ±10% |
| RBPlats | R 17 365 253.00 | R 89 939 868.00 | ±25% |
| Fraser Alexander | R 0.00 | R 812 777.00 | Unknown |
| RBN Entities | R 3 323 519.00 | R 21 427 968.00 | ±40% |