# RBA OPMO Monthly Makgotla Report – June 2016

# Community Events scheduled in the coming month

# (1/6/2016 – 30/6/2016)

| Event Name | Region | Date |
| --- | --- | --- |
| Primary Schools Cross Country | Capital | Saturday, 4 June 2016 |
| Royal Bafokeng Jr. NBA/WNBA Basketball Primary League Tournament | All regions | Saturday, 4 June 2016 |
| HSDS: Letsema (Community Outreach, Youth Programme) | North | Friday, 24 June 2016 |
| RBED: Farmers market session | Capital | Saturday, 25 June 2016 |

# Big Projects (Currently Active)

# (As at 13/6/2016)

| Project Name | Responsible Department | Budget Source | Progress % | End date | Region; Village |
| --- | --- | --- | --- | --- | --- |
| Establishment of OVC (Orphans & Vulnerable Children) in Luka | HSDS | External Funding | 45.8% | 23 June 2016 | North; Luka |
| Monitoring Tlaseng Construction of Roads & Storm Water Drainage Phase 3 | Infrastructure Maintenance (IDP project) | RLM | 90.5% | 31 May 2016 | North East; Tlaseng |
| Monitoring Construction of a Road in Tsitsing & Storm Water Drainage | Infrastructure Maintenance (IDP project) | RLM | 90.1% | 31 May 2016 | North East; Tsitsing |
| Focused Approach -Enterprise Development Phase 1 | RBED | External Funders | 55.7% | 30 December 2017 | All |
| Establishment of Play Therapy Room | HSDS | RBN | 89.1% | 7 August 2016 | Capital; Phokeng |
| Land Policy Development | Traditional Governance | RBN | 85.2% | 8 August 2016 | All |
| Establishment of mini market in RBN | Land Use & Agriculture | RBN | 59.4% | 29 July 2016 | North & Capital; Luka & Phokeng |
| Plan 35 Development | GCOO | RBN | 51.6% | 19 November 2016 | All |
| Establishment and Management of the animal pound/feedlot in Bafokeng | Land Use & Agriculture | RBN | 63.7% | 15 July 2016 | North East; Tlaseng |
| Installation of Boreholes and windmills 2015 | Land Use & Agriculture | RBN | 70.9% | 31 May 2016 | North; North East; Central; Capital; Luka, Phokeng, Tlaseng, Marakana & Mosenthal, Mogojane |
| FNB I Homes | Moumo | FNB | 50.6% | 26 September 2016 | North, Luka |
| Preparations for Olympics Rio 2016 | RBS | RBN | 69% | 29 July 2016 | Capital; Phokeng, Lefaragatlha |
| Monitoring the Construction of High-mast Lighting in RBN Villages (IDP project) | Infrastructure Maintenance | RLM | 6% | 12 August 2016 | North, Central, South East; Kanana, Seutube, Marakana & Mosenthal, Mabitse, Tlapa & Tlapa East, Rasimone, Lesung, Mafika, Robega |
| Marketing for Bafokeng Tourism Establishments | RBED | RBN | 40.7% | 11 August 2016 | All |

# Projects scheduled to start in the coming month

# (1/6/2016 – 30/6/2016)

| Project Name | Responsible Department | Budget Source | Planned Benefits | Region |
| --- | --- | --- | --- | --- |
| PULA 2016 | Research | RBN & External Funders | Database of land use and stand information and information on most critical community needs to inform decision making and planning | All |

# Projects completed in the previous month

# (1/4/2016 – 30/4/2016)

| Project Name | Responsible Department | Budget Source | Actual/ Realised Benefits | Region |
| --- | --- | --- | --- | --- |
| Monitoring Kanana Upgrade of Roads & Storm Water Drainage | Infrastructure Maintenance | RLM | 2.4kms of new roads paved | Central; Kanana |
| Video Shooting for Mama Mimi Co-operatives | RBED | RBN | Increased funding opportunities to 6 SMMEs through showcasing in the video. 1 local SMME appointed to execute the project. | Capital, Central, North, North East, South East; Phokeng, Kanana, Tlaseng, Mamerotse, Chaneng |
| Recording of Subdivided Stands in Capital Region | Infrastructure Maintenance | RBN | All subdivisions recorded. To have full representation of what exists on the ground. | Capital; Phokeng, Kgale, Lefaragatlha, Bobounja, Lenatong |

# RBN Entities Procurement Spend on Local SMMEs

|  | Procurement Spend |  |
| --- | --- | --- |
|  | April only | Year-to-date (Jan – Apr) |
| January – March | R 1 444 876.00 | R 10 410 228.00 |