# RBA OPMO Monthly Makgotla Report – October 2016

# Community Events scheduled in the coming month

# (1/10/2016 – 29/10/2016)

| Event Name | Region | Date |
| --- | --- | --- |
| Bakwena Lifestyle 5km Fun run/walk | North | Saturday, 15 October 2016 |
| Arts & Culture: Heritage Trail | All | Saturday, 1 October 2016 |
| RBED: Farmers market session | Capital | Saturday, 29 October 2016 |
| RBS Metshameko: Primary Schools Football & Netball League Quarter Finals | North | Saturday, 22 October 2016 |
| RBS Metshameko: Primary Schools Football & Netball League Semi Finals | North | Saturday, 22 October 2016 |
| RBS Metshameko: Primary Schools Football & Netball League Championships | North | Saturday, 22 October 2016 |
| RBS Metshameko: Primary Schools Football & Netball League Championships | North | Saturday, 22 October 2016 |
| RBS: Jr NBA/WNBA Basketball Finals | Capital | Saturday, 29 October 2016 |
| HSDS: Letsema (People with Disability) | North | Friday, 28 October 2016 |

# Big Projects (Currently Active)

# (As at 15/9/2016)

| Project Name | Responsible Department | Budget Source | Progress % | End date | Region; Village |
| --- | --- | --- | --- | --- | --- |
| Population and Use of Land Audit (PULA) 2016 | Research | RBN & External Funders | 35.8% | 23 May 2017 | All |
| Focused Approach -Enterprise Development Phase 1 | RBED | External Funders | 60.8% | 30 December 2017 | All |
| Land Policy Development | Traditional Governance | RBN | 88.1% | 30 September 2016 | All |
| Establishment of cooperatives at the sheltered employment centre | HSDS | RBN | 70.4% | 6 September 2016 | Capital; Lefaragathla |
| Establishment of mini market in RBN | Land Use & Agriculture | RBN | 61.3% | 12 October 2016 | North & Capital; Luka & Phokeng |
| Plan 35 Development | GCOO | RBN | 77.3% | 19 November 2016 | All |
| Establishment and Management of the animal pound/feedlot in Bafokeng | Land Use & Agriculture | RBN | 61.3% | 17 October 2016 | North East; Tlaseng |
| Lefaragathle Old Pump House Upgrade | Infrastructure Maintenance | RBN | 39% | 21 October 2016 | Capital; Lefaragathla |
| Monitoring the Standard Bank Housing Project | Infrastructure Maintenance | RLM | 94.4% | 30 September 2016 | North, Capital; Luka, Mogono, Phokeng, Kgale |
| Monitoring the Construction of High-mast Lighting in RBN Villages (IDP project) | Infrastructure Maintenance | RLM | 94.6% | 29 September 2016 | North, Central, South East; Kanana, Seutube, Marakana & Mosenthal, Mabitse, Tlapa & Tlapa East, Rasimone, Lesung, Mafika, Robega |
| Monitoring the Construction of Road and Stormwater in Magokgwane (IDP project) | Infrastructure Maintenance | RLM | 60.1% | 13 October 2016 | Capital; Phokeng |
| Monitoring the Construction of Road and Stormwater in Lenatong (IDP project) | Infrastructure Maintenance | RLM | 59.8% | 14 October 2016 | Capital; Lenatong |
| Marketing for Bafokeng Tourism Establishments | RBED | RBN | 73.8% | 15 January 2016 | All |
| Establishment of Community and Nutrition and Development Center (CNDC) Project | HSDS | RBN | 26.1% | 31 March 2017 | Central, Capital; Kanana, Lefaragatlha |
| Kimberley pilgrimage | Arts & Culture | RBN | 96.5% | 12 October 2016 | All |
| Establishment of a wound clinic within Mfidikwe and Thekwane Health Centre | HSDS | RBN | 93.6% | 18 November 2016 | South East; Thekwane, Mfidikwe |
| Marriage seminar (Couples Retreat) 2016 | HSDS | RBN | 96.10% | 28 September 2016 |  |

# Projects scheduled to start in the coming month

# (1/10/2016 – 29/10/2016)

| Project Name | Responsible Department | Budget Source | Planned Benefits | Region |
| --- | --- | --- | --- | --- |
| Kgotha Kgothe November 2016 | Traditional Governance | RBN | 3000 Community members expected to attend; 12 Local SMMEs appointed | Capital; Phokeng |

# Projects completed in the previous month

# (1/9/2016 – 30/9/2016)

| Project Name | Responsible Department | Budget Source | Actual/ Realised Benefits | Region; Village |
| --- | --- | --- | --- | --- |
| Monitoring Construction of a Road in Tsitsing & Storm Water Drainage (IDP project) | Infrastructure Maintenance (IDP project) | RLM | 1.8 km of new surfaced roads | North East; Tsitsing |
| Annual Royal Bafokeng Boys and Girls Basketball Tournament 2016 | RBS | RBN | NVR | Capital; Phokeng |

RBN Tender opportunities

# (1/10/2016 – 29/10/2016)

| Opportunity Detail | Date |
| --- | --- |
| No confirmed tender opportunities for October |  |

# Procurement Spend on Local SMMEs by mines and RBN Entities

|  | Procurement Spend |  |  |
| --- | --- | --- | --- |
|  | August only | Year-to-date (Jan – August) | % of total Procurement Spend (YTD) |
| Impala | R 0.00 | R194 608 837.00 | Unknown |
| RBPlats | R 14 149 662.00 | R121 092 751.90 | Unknown |
| Fraser Alexander | R 0.00 | R 812 777.00 | Unknown |
| RBN Entities | R 4 342 835.00 | R 29 825 907.00 | ±15% |