# RBA OPMO Monthly Makgotla Report – December 2016

Kitsiso go Batsha ba RBN: Ka kopo romela CV go Disipi@bafokensgports.com gore o tsene mo RBN Database. RBA yona e tla romela di CV tse di maleba go menyetla eo ba tsibosiwang ka yona.

# Community Events scheduled in the coming month

# (1/12/2016 – 31/12/2016)

| Event Name | Region | Date |
| --- | --- | --- |
| Bakwena Lifestyle 5km Fun run/walk | North East | Saturday, 10 December 2016 |

# Big Projects (Currently Active)

# (As at 14/12/2016)

| Project Name | Responsible Department | Budget Source | Progress % | End date | Region; Village |
| --- | --- | --- | --- | --- | --- |
| Population and Use of Land Audit (PULA) 2016 | Research | RBN & External Funders | 47.3% | 23 May 2017 | All |
| RBED/CCBSA Youth Entrepreneurship Programme | RBED | Coca Cola | 20% | 30 April 2017 | All |
| Focused Approach -Enterprise Development Phase 1 | RBED | External Funders | 64.3% | 30 December 2017 | All |
| Land Policy Development | Traditional Governance | RBN | 90.7% | 15 December 2016 | All |
| Establishment of mini market in RBN | Land Use & Agriculture | RBN | 98% | 25 November 2016 | North & Capital; Luka & Phokeng |
| Establishment and Management of the animal pound/feedlot in Bafokeng | Land Use & Agriculture | RBN | 50.4% | 27 March 2017 | North East; Tlaseng |
| Education Policy Development | Traditional Governance | RBN | 57.8% | 28 March 2016 | All |
| Lefaragathle Old Pump House Upgrade | Infrastructure Maintenance | RBN | 92.2% | 9 December 2016 | Capital; Lefaragathla |
| Marketing for Bafokeng Tourism Establishments | RBED | RBN | 98.6% | 7 December 2016 | All |
| Monitoring the Construction of High-mast Lighting in RBN Villages (IDP project) | Infrastructure Maintenance | RLM | 84.9% | 31 January 2017 | North, Central, South East; Kanana, Seutube, Marakana & Mosenthal, Mabitse, Tlapa & Tlapa East, Rasimone, Lesung, Mafika, Robega |
| Monitoring the Construction of Road and Stormwater in Magokgwane (IDP project) | Infrastructure Maintenance | RLM | 67.4% | 13 December 2016 | Capital; Phokeng |
| Monitoring the Construction of Road and Stormwater in Lenatong (IDP project) | Infrastructure Maintenance | RLM | 76.3% | 9 December 2016 | Capital; Lenatong |
| Establishment of Community and Nutrition and Development Centre (CNDC) Project | HSDS | RBN | 71.3% | 31 March 2017 | Central, Capital; Kanana, Lefaragatlha |
| Construction of swimming pool complex | Lebone | External Funding | 62.7% | 25 April 2017 | Capital; Phokeng |
| Establishment of the Youth in school programme | HSDS | RBN | 92.2% | 13 December 2016 | All |
| Establishment of RBED Satellite Office -South East | RBED | RBN | 50.5% | 2 December 2016 | South East; Thekwane |

# Projects scheduled to start in the coming month

# (1/12/2016 – 31/12/2016)

| Project Name | Responsible Department | Budget Source | Planned Benefits | Region |
| --- | --- | --- | --- | --- |
| No new projects are scheduled to start in November 2016 |  |  |  |  |

# Projects completed in the previous month

# (1/10/2016 – 31/10/2016)

| Project Name | Responsible Department | Budget Source | Actual/ Realised Benefits | Region; Village |
| --- | --- | --- | --- | --- |
| Kimberley pilgrimage 2016 | Arts & Culture | RBN | 365 individuals attended the pilgrimage to Kimberley. Commemoration of forefathers working in Kimberley | All |
| Commemoration of International Day of Older Persons 2016 | HSDS | RBN | 34 individuals attending the event. Improvement in care for the aged | Capital; Phokeng |
| Royal Bafokeng Jr NBA/Jr WNBA League finals 2016 | RBS | RBN | 10000+ youth participated in the event and 14 local SMMEs benefitted from the project | All |

RBN Tender opportunities

# (1/12/2016 – 31/12/2016)

| Opportunity Detail | Date |
| --- | --- |
| Tender for installation of pre-paid meters: Water Conservation and Water Demand Management System improvement through the procurement of prepaid water meters | 15 December 2015 |

# Procurement Spend on Local SMMEs by mines and RBN Entities

|  | Procurement Spend |  |  |
| --- | --- | --- | --- |
|  | October only | Year-to-date (Jan – Oct) | % of total Procurement Spend (YTD) |
| Impala | R189 943 197.00 | R384 552 034.00 | Unknown |
| RBPlats | R 17 068 440.00 | R155 281 692.00 | Unknown |
| Fraser Alexander | R 0.00 | R 812 777.00 | Unknown |
| RBN Entities | R 3 073 543.00 | R 38 983 160.00 | ±40% |