# RBA OPMO Monthly Makgotla Report – January 2017

Kitsiso go Batsha ba RBN: Ka kopo romela CV go Disipi@bafokensgports.com gore o tsene mo RBN Database. RBA yona e tla romela di CV tse di maleba go menyetla eo ba tsibosiwang ka yona.

# Community Events scheduled in the coming month

# (1/1/2017 – 31/1/2017)

| Event Name | Region | Date |
| --- | --- | --- |
| Bakwena Lifestyle 5km Fun run/walk | Central | Saturday, 28 January 2017 |

# Big Projects (Currently Active)

# (As at 14/12/2016)

| Project Name | Responsible Department | Budget Source | Progress % | End date | Region; Village |
| --- | --- | --- | --- | --- | --- |
| Population and Use of Land Audit (PULA) 2016 | Research | RBN & External Funders | 79.60% | 23 May 2017 | All |
| RBED/CCBSA Youth Entrepreneurship Programme | RBED | Coca Cola | 20% | 2 June 2017 | All |
| Focused Approach -Enterprise Development Phase 1 | RBED | External Funders | 66% | 30 December 2017 | All |
| Land Policy Development | Traditional Governance | RBN | 93.10% | 30 January 2017 | All |
| Establishment of mini market in RBN | Land Use & Agriculture | RBN | 98% | 28 February 2016 | North & Capital; Luka & Phokeng |
| Establishment and Management of the animal pound/feedlot in Bafokeng | Land Use & Agriculture | RBN | 50.4% | 27 March 2017 | North East; Tlaseng |
| Education Policy Development | Traditional Governance | RBN | 57.8% | 28 March 2017 | All |
| Lefaragathle Old Pump House Upgrade | Infrastructure Maintenance | RBN | 92.2% | 7 April 2017 | Capital; Lefaragathla |
| Monitoring the Construction of High-mast Lighting in RBN Villages (IDP project) | Infrastructure Maintenance | RLM | 84.9% | 31 January 2017 | North, Central, South East; Kanana, Seutube, Marakana & Mosenthal, Mabitse, Tlapa & Tlapa East, Rasimone, Lesung, Mafika, Robega |
| Monitoring the Construction of Road and Storm water in Magokgwane (IDP project) | Infrastructure Maintenance | RLM | 70.50% | 31 January 2017 | Capital; Phokeng |
| Monitoring the Construction of Road and Storm water in Lenatong (IDP project) | Infrastructure Maintenance | RLM | 79.60% | 31 January 2017 | Capital; Lenatong |
| Establishment of Community and Nutrition and Development Centre (CNDC) Project | HSDS | RBN | 75.40% | 31 March 2017 | Central, Capital; Kanana, Lefaragatlha |
| Construction of swimming pool complex | Lebone | External Funding | 62.7% | 25 April 2017 | Capital; Phokeng |
| Establishment of the Youth in school programme | HSDS | RBN | 98.10% | 31 January 2017 | All |
| Establishment of RBED Satellite Office -South East | RBED | RBN | 63.60% | 31 January 2017 | South East; Thekwane |

# Projects scheduled to start in the coming month

# (1/1/2017 – 31/1/2017)

| Project Name | Responsible Department | Budget Source | Planned Benefits | Region |
| --- | --- | --- | --- | --- |
| No new projects are scheduled to start in January 2017 |  |  |  |  |

# Projects completed in the previous month

# (1/112/2016 – 31/12/2016)

| Project Name | Responsible Department | Budget Source | Actual/ Realised Benefits | Region; Village |
| --- | --- | --- | --- | --- |
| Marketing for Bafokeng Tourism Establishments | RBED | RBN | 7 Bafokeng SMMEs assisted with marketing their businesses | All |

RBN Tender opportunities

# (1/1/2017 – 31/1/2017)

| Opportunity Detail | Date |
| --- | --- |
| No tender opportunities identified for January 2017 |  |

# Procurement Spend on Local SMMEs by mines and RBN Entities

|  | Procurement Spend |  |  |
| --- | --- | --- | --- |
|  | November only | Year-to-date (Jan – Nov) | % of total Procurement Spend (YTD) |
| Impala | R 93 617 949.00 | R478 169 983.00 | Unknown |
| RBPlats | R 19 798 248.00 | R175 079 940.00 | Unknown |
| Fraser Alexander | R 0.00 | R 812 777.00 | Unknown |
| RBN Entities | R 7 866 599.00 | R 46 849 759.00 | ±40% |