## Risk Evaluation
Risk Area |  | Impact |  | Risk Response
| Occurrence/ Likelihood | H/M/L | Priority Total | Mitigate / Deflect / Eliminate / Accept
| 1-10 | 1-10 | Likelihood x Impact
More groups want to participate | 5 | 5 | 25 | Accept
| 6 | 6 | 36 | Accept
| 5 | 5 | 25 | Accept
| 5 | 6 | 30 | Accept
0
0
0
0
0
0
0
0
0

## Stakeholder
Stakeholder | Needs & Expectations | Predictability (1-5) | Power (1-5) | Total | Priority
|  | Where 1 is very predictable and 5 is not predictable at all) | Where1 is not powerful and 5 is very powerful) | (Predictability x power)
RBN Youth |  | 2 | 3 | 6
Elderly People |  | 3 | 2 | 6
Royal Bafokeng Sports |  | 2 | 3 | 6
Royal Bafokeng Institute |  | 2 | 3 | 6
People with Dissability |  | 3 | 2 | 6
Ophans and Vulnerable Children |  | 3 | 2 | 6
Treasury |  | 1 | 5 | 5
0
0

## Milestones
Project | Project Name | Scope | Indicators for project | Project Manager | Baseline Target Date
| Milestone Name | Milestone Description | Indicator | Responsible Person | Baseline Target Date
e.g. 3/06/2010
Milestone 1 | Organize Venue | Book a venue which can accommodate 500 people, it should have electricity water and sanitation | Veneu booked and available | Gabriel Lenkwe
Milestone 2 | Organize Artists | Identify 10 cultural groups from 5 RBN Regions and 10 hip hop and dance groups. | 20 groups available and briefed. | Gabriel Lenkwe
Milestone 3 | Organize Transport | Book 2 buses to transport artists and other participants to the venue. | Transport booked and available | Gabriel Lenkwe
Milestone 4 | Organize Auditions | Conduct auditions in 5 RBN regions for groups to perform during the festival. | Auditions held in 5 regions and groups selected for the festival. | Gabriel Lenkwe
Milestone 5 | Organize sound system | book a sound system that can be used inside for an audience of plus minus 1000 people. | sound system booked and available. | Gabriel Lenkwe
Milestone 6 | Marketing | Develop flyers and burners to be placed in all Bafokeng villages | flyers and Burners available | Gabriel Lenkwe
Milestone 7 | Organize Guests | Develop invitations to Supreme Cousil, counselors and relevant stake holders. | Invitations drafted available | Gabriel Lenkwe
Milestone 8 | Program | Draft a progam for the day | Program available | Gabriel Lenkwe
Milestone 9 | Organize Security and EMS | Make a presentation to EMS and Reaction Force | Both EMS and Reaction Force available | Gabriel Lenkwe
Milestone 10 | Organize gathering act permission | Apply for gathering act at Rustenburg Public Safety Department | Application form filled and submitted | Gabriel Lenkwe

## Activity
Project Name: Youth Festival
Activity Sheet
Nr | Task | Activity | Duration | Start | End | Predecessors | Resources | Responsibility | Cost
1 | Organize Venue | [7 empty] | 0
1.1 |  | Check if Bafokeng Civic Center is available |  | 23/07/10 | 23/07/10 |  |  |  | 0
1.1.1 |  | Make a booking |  | 23/07/10 | 23/07/10 |  |  |  | 0
|  | Confirm booking with Mr Tshose/Katane |  | 24/07/10 | 24/07/10 |  |  |  | 0
|  | Book venue for Rehearsals |  | 22/8/2010 | 22/8/2010 |  |  |  | 0
2 | Organize Transport | [7 empty] | 0
2.1 |  | Check if transport is available with the transport officer |  | 2010-10-08 | 2010-10-08 |  |  |  | 0
2.2 |  | Check if budget is available | 1 Day | 2010-12-08 | 2010-12-08
2.2.1 |  | Make transport requisition | 1day | 19/7/2010 | 19/7/10 |  |  |  | 0
2.3 |  | Seek approval from management | 1day | 14/8/2010 | 14/8/2010
2.3.1 |  | Submit requisition to transport office | 1day | 14/8/2010 | 14/8/2010 |  |  |  | 0
2.4 |  | Confirm booking of transport | 1day | 20/8/2010 | 20/8/2010 |  |  |  | 0
0
0
0
3 | Organize Catering | [7 empty] | 0
3.1 |  | Check if the budget is available | 1 day | 2010-10-08 | 2010-10-08 |  |  |  | 0
3.1.1 |  | Submit catering requisition for approval | 1 day | 13-08-10 | 13-08-10
3.1.2 |  | Design the menu | 1 day | 2010-10-08 | 2010-10-08
3.2 |  | Submit requisition to procument | 1 day | 2010-12-08 | 2010-12-08 |  |  |  | 0
3.3 |  | Await quotations | 1 day | 19/8/2010 | 19/8/2010 |  |  |  | 0
3.4 |  | Confirmation with the procurement | 1 day | 28/8/2010 | 28/8/2010 |  |  |  | 0
0
4 | Invite guest Speakers | [7 empty] | 0
4.1 |  | Compile VIP Guestlist | 3 days | 22/8/2010 | 25/8/2010 |  |  |  | 0
4.2 |  | Send invite | 3days | 24/8/2010 | 26/8/2010
4.3 |  | Design invites | 3 days | 17/8/2010 | 19/8/2010
4.3.1 |  | Procure designer | 11 days | 13/8/2010 | 23/8/2010
|  | email invite | 1 day | 27/8/2010 | 27/8/2010 |  |  |  | 0
|  | Receive RSVP responses | 2 weeks | 27/8/2010 | 2010-10-09
5 | Program | [7 empty] | 0
5.1 |  | Design the Program |  | 2010-10-08 | 2010-10-08
5.1.1 |  | draft the program |  | 2010-05-08 | 2010-05-08 |  |  |  | 0
5.1.2 |  | Submit it to the manager for comments and inputs |  | 2010-10-08 | 2010-10-08 |  |  |  | 0
5.2 |  | Make a final program |  | 13/8/2010 | 13/8/2010
5.3 |  | email/send the program to key people |  | 24/8/2010 | 24/8/2010
6 | Organize equipment | [7 empty] | 0
6.1 |  | Make a list of all equipment needed |  | 17/8/2010 | 17/8/2010 |  |  |  | 0
6.2 |  | Check with role players which resources they will need |  | 31/8/2010 | 31/8/2010 |  |  |  | 0
6.3 |  | Check the availability of equipment |  | 2010-02-09 | 2010-09-02
|  | Check if equipment is on good condition |  | 2010-02-09 | 2010-09-02
7 | Organize artists | [7 empty] | 0
7.1.1 |  | Identify artists |  | 2010-10-08 | 13/8/2010
7.1 |  | Draft contracts |  | 13/8/2010 | 13/8/2010 |  |  |  | 0
7.2 |  | Invite artists to a meeting |  | 18/8/2010 | 18/8/2010
7.3 |  | Meeting with artists |  | 20/8/2010 | 20/8/2010
|  | Sign Contracts |  | 2010-09-01 | 2010-09-03 |  |  |  | 0
0
8 | Organize Public Gathering Permission | [7 empty] | 0
8.1 |  | Draft a letter to Public Safety | 1 day | 2010-02-08 | 2010-02-08 |  |  |  | 0
8.1.1 |  | Send to HSDS management for approval | 1 day | 2010-02-08 | 2010-02-08 |  |  |  | 0
8.2 |  | Consult with office of CEO for approval | 1 day | 2010-03-08 | 2010-03-08 |  |  |  | 0
8.3 |  | Send the letter to Public Safety | 1 day | 2010-05-08 | 2010-05-08 |  |  |  | 0
8.4 |  | Await a response for a meeting | 1 day | 13/8/2010 | 13/8/2010 |  |  |  | 0
8.5 |  | Attend a briefing at Public Safety | 1 day | 20/8/2010 | 20/8/2010 |  |  |  | 0
8.6 |  | Collect a permition from Public Safety | 1 day | 20/8/2010 | 20/8/2010 |  |  |  | 0
0
9 | Marketing | [7 empty] | 0
9.1 |  | Identify service providers/establish a marketing team | 1day | 25/8/2010 | 25/8/2010 |  |  |  | 0
9.2 |  | Procure Designers | 1day | 2010-01-09 | 2010-01-09 |  |  |  | 0
9.3 |  | Design of flyers and posters | 3days | 2010-03-09 | 2010-06-08
9.4 |  | Put up posters and distribution of flyers | 3 days | 11//9/2010 | 13/9/2010
Total | [8 empty] | 0

## Gantt
Project Name: Youth Arts Festival
GANTT Chart
[9 empty] | Week | [6 empty] | Week | [6 empty] | Week | [6 empty] | Week | [6 empty] | Week | [6 empty] | Week | [6 empty] | Week | [6 empty] | Week
Nr | Task | Activity | 2010-07-20 | 2010-07-21 | 2010-07-22 | 2010-07-23 | 2010-07-24 | 2010-07-25 | 2010-07-26 | 2010-07-27 | 2010-07-28 | 2010-07-29 | 2010-07-30 | 2010-07-31 | 2010-08-01 | 2010-08-02 | 2010-08-03 | 2010-08-04 | 2010-08-05 | 2010-08-06 | 2010-08-07 | 2010-08-08 | 2010-08-09 | 2010-08-10 | 2010-08-11 | 2010-08-12 | 2010-08-13 | 2010-08-14 | 2010-08-15 | 2010-08-16 | 2010-08-17 | 2010-08-18 | 2010-08-19 | 2010-08-20 | 2010-08-21 | 2010-08-22 | 2010-08-23 | 2010-08-24 | 2010-08-25 | 2010-08-26 | 2010-08-27 | 2010-08-28 | 2010-08-29 | 2010-08-30 | 2010-08-31 | 2010-09-01 | 2010-09-02 | 2010-09-03 | 2010-09-04 | 2010-09-05 | 2010-09-06 | 2010-09-07 | 2010-09-08 | 2010-09-09 | 2010-09-10 | 2010-09-11 | 2010-09-12 | 2010-09-13
1 | Organize Venue | 0
1.1 | 0 | Check if Bafokeng Civic Center is available
1.1.1 | 0 | Make a booking
0 | 0 | Confirm booking with Mr Tshose/Katane
0 | 0 | Book venue for Rehearsals
2 | Organize Transport | 0
2.1 | 0 | Check if transport is available with the transport officer
2.2.1 | 0 | Make transport requisition
2.3.1 | 0 | Submit requisition to transport office
2.4 | 0 | Confirm booking of transport
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
3 | Organize Catering | 0
3.1 | 0 | Check if the budget is available
3.1.2 | 0 | Design the menu
3.2 | 0 | Submit requisition to procument
3.3 | 0 | Await quotations
3.4 | 0 | Confirmation with the procurement
0 | 0 | 0
4 | Invite guest Speakers | 0
4.1 | 0 | Compile VIP Guestlist
4.2 |  | Send invite
4.3 |  | Design invites
4.3.1 |  | Procure Designers
0 |  | Email invites
0 | 0 | Receive RSVP responses
5 | Program | 0
Design program
5.1.1 | 0 | draft the program
Email program to key people
Submit it to the manager for comments and inputs
5.1.2 | 0 | Make a final program
6 | Organize equipment | 0
6.1 | 0 | Make a list of all equipment needed
Check the availability of resources
6.2 | 0 | Check with role players which resources they will need
7 | Organize artists | 0
7.1 | 0 | Draft contracts
0 | 0 | Sign Contracts
0 | 0 | 0
8 | Organize Public Gathering Permission | 0
8.1 | 0 | Draft a letter to Public Safety
8.1.1 | 0 | Send to HSDS management for approval
0 | 0 | Consult with office of CEO for approval
8 | Organize Public Gathering Permission | 0
8.1 | 0 | Draft a letter to Public Safety
8.1.1 | 0 | Send to HSDS management for approval
8.2 | 0 | Consult with office of CEO for approval
8.3 | 0 | Send the letter to Public Safety
8.4 | 0 | Await a response for a meeting
8.5 | 0 | Attend a briefing at Public Safety
8.6 | 0 | Collect a permition from Public Safety
0 | 0 | 0
9 | Marketing | 0
9.1 | 0 | Identify service providers/establish a marketing team
9.2 | 0 | Procure Designers
Design of flyers and posters
Put up posters and distribution of flyers

## Budget
Project Name
PROJECT COST TRACKING TEMPLATE
| DEVELOPMENT COST | UNIT COST R | QUANTITY | TOTAL BUDGET | Month 1 | month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
| Budget Balance Brought Forward |  |  | 165750 | 165750 | 154719 | 154719 | 154719 | 154719 | 154719 | 154719 | 154719 | 154719 | 154719 | 154719 | 154719
CAPEX |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LIST CAPEX EXPENCES |  | 3 | 0
|  |  | 15 | 0
|  | 0 | 1 | 0
|  | 0 | 1 | 0
|  | 0 | 1 | 0
|  | 0 | 1 | 0
|  | 0 | 1 | 0
|  | 0 | 1 | 0
OPEX |  |  |  | 165750 | 11031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LIST OPEX EXPENCES | 0 | 1
| Plenary meeting (10 people x 3 days) | 50 | 30 | 1500
| 4 buses x 1 day | 5000 | 5 | 25000 | Month 1: 11031
| Stage x 1 day | 20000 | 1 | 20000
| Catering (1000 people x 1 day) | 50 | 800 | 40000
| Performance fee (15 groups x 1 day) | 2000 | 15 | 30000
| Auditions (5 judges x 5 days) Regionally | 50 | 25 | 1250
| Guest artist ( 1 group x 1 day) | 20000 | 1 | 20000
| Décor ( traditional x 1 day) | 5000 | 1 | 5000
| Marketing (flyers and burners) Radio adverts | 23000 | 1 | 23000
OTHER |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LIST OTHER EXPENCES | 0 | 1 | 0
|  | 0 | 1 | 0
|  | 0 | 1 | 0
|  | 0 | 1 | 0
|  | 0 | 1 | 0
TOTAL DEVELOPING COST (EXCLUDING VAT) |  |  |  | 165750 | 11031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Compatibility Report
Compatibility Report for Activity Chart.xls
Run on 4/8/2010 15:37
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 110